## Agile Project Plan
| PROJECT NAME | PROJECT LEADER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | A payment processing plugin to accept Bitcoin
| Pay-a-Bit | Darshan Shah | 2018-09-01 | 2019-03-31 |  | 10% |  | SCOPE STATEMENT | To add the main funcionality of proccessing Bitcoin payments.
As a | User Story | FEATURE TYPE | RESPONSIBLE | Prioritization | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Merchant | I want to accept Bitcoin |  | All team | 1 | 6-09-2018 | 2018-12-06 | 96 | Started
Customer | I want to have a well-formed and clean UI design, |  | All team | 2 | 6-10-2018 | 2018-12-06 | 66 | Started
Customer | I want to have a QR code to make payment easier |  | All team | 3 | 6-10-2018 | 2018-12-06 | 60 | Started
Merchant | I want to have a dashboard with transaction status and order history |  | All team | 4 | 6-10-2018 | 2018-12-06 | 60 | Started
Customer | I want to have a receipt for the transaction, |  | All team | 5 | 6-11-2018 | 2018-12-06 | 30 | Not Started