## Sheet1
Hours of Work remaining each two days in 14 days sprint
BackLog Item | Task | Task Owner | Initial Estimation | Day 1&2 | Day 3&4 | Day 5&6 | Day 7&8 | Day 9&10 | Day 11&12 | Day 13&14
Allow merchant to accept the cryptocurrency | Design the prototype of user interface to receive user data for landing page | Neel | 2 | 3 | 2 | 1 | 0
| Figure out the APIs for the different Cryptocurrencies. | Darshan | 3 | 4 | 3 | 2 | 1 | 0
| Make merchant accept the liabilities of using the app | Darshan | 4 | 4 | 3 | 2 |  | 1 | 0
| Implement code to send the input data from the user to the database table with client side and server side validation | Darshan | 5 | 5 | 4 | 3 | 2 | 1 | 0
| Write unit test for all data | Jaydeep | 4 | 4 | 3 | 2 | 1 | 0
I want to have a well-formed and clean UI design | Design the prototype of user interface which will be simple and easy to use | Neel | 3 | 3 | 2 | 1 | 0
| Implementing WordPress coding styles for the plugin | Akaash | 4 | 4 | 3 | 2 | 1 | 0
| Generating QR codes for making transaction process easier for customers | Akaash | 5 | 5 | 4 | 3 | 2 | 1 | 0
| Implement code to confirm transaction. | Akaash | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Write unit test for all data | Jaydeep | 4 | 4 | 3 | 2 | 1 | 0
Allow buyer to have a receipt for the transaction. | Creating user interface for accessible and informative reciepts. | Neel | 4 | 4 | 3 | 2 | 1 | 0
| Pulling out data from database and generating receipts. | Akaash | 4 | 4 | 3 | 2 | 1 | 0
| Implement code to print or share the receipt on email. | Darshan | 6 | 6 | 4 | 3 | 2 | 1 | 0
| Write unit test for all data | Jaydeep | 4 | 4 | 3 | 2 | 1 | 0
A dashboard with sales graph and product insights for the merchant | Design the prototype of user interface to display sales data for dashboard. | Neel | 2 | 2 | 1 | 0
| Implement code to style dashboard for sales. | Neel | 3 | 3 | 2 | 1 | 0
| Implement code to use sales data and display it as graphs and other statistical analytics | Jaydeep | 4 | 4 | 3 | 2 | 1 | 0
| Write unit test for all data | Jaydeep | 4 | 4 | 3 | 2 | 1 | 0
Confirmation to verify that the transaction is complete. | Creating a waiting page while the transaction is being processed. | Darshan | 2 | 2 | 1 | 0
| Design the page for estimated time for the transaction | Jaydeep | 2 | 2 | 1 | 0
| Implement code at back-end for transaction approval | Jaydeep | 3 | 3 | 2 | 1 | 0
| Implement code to accomplish functionality for user Interface using google API | Darshan | 4 | 4 | 3 | 2 | 1 | 0
| Implement code for front end styles on output result | Neel | 4 | 4 | 3 | 2 | 1 | 0
| Write unit tests for both pages | Darshan | 4 | 5 | 4 | 3 | 2 | 1 | 0
I want to have an easy secure crypto transaction. | Design the prototype for payment page. | Neel | 3 | 3 | 2 | 1 | 0
| Adding QR code for public address and making the process error free. | Akaash
| Design the prototype for payment confirmation page. | Neel | 3 | 3 | 2 | 1 | 0
| Implement the code to style the payment page with client side validation. | Neel | 4 | 4 | 3 | 2 | 1 | 0
| Implement the code to style payment confirmation page. | Akaash | 4 | 4 | 3 | 2 | 1 | 0
| Implement the code to accomplish the functionality for payment page. | Jaydeep | 5 | 4 | 3 | 2 | 1 | 0
| Implement the code to accomplish the functionality for payment confirmation page. | Darshan | 4 | 4 | 3 | 2 | 1 | 0
| Write unit tests for payment page for both server and client side. | Jaydeep | 4 | 4 | 4 | 3 | 2 | 1 | 0